## ProjectSchedule
GANTT Chart
Project Manager: Solanki Vaibhav
Team: 4 |  | 2019-06-17
|  | 1 |  |  | 2019-06-19 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15
[5 empty] | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21
TASK | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Understanding the Client Background | 100% | 2019-06-17 | 2019-06-18 | 2
Understanding the Clients Problem | 100% | 2019-06-17 | 2019-06-18
Creating list of Questions | 100% | 2019-06-18 | 2019-06-18
Developing the RFI Doc | 100% | 2019-06-18 | 2019-06-18
Reviewing the RFI Doc | 100% | 2019-06-18 | 2019-06-19
Finalizing the RFI Doc | 100% | 2019-06-19 | 2019-06-19
CDL History | 100% | 2019-06-21 | 2019-06-25 | 5
Actor/ Roles / Person involved | 100% | 2019-06-21 | 2019-06-25 | 5
CDL business challenges | 100% | 2019-06-21 | 2019-06-25
CDL brand and its status | 100% | 2019-06-21 | 2019-06-25
AS-IS Principle and KPI | 100% | 2019-06-21 | 2019-06-25
Reviewing the Client Background Docs | 100% | 2019-06-26 | 2019-06-26
Finalizing the Docs | 100% | 2019-06-26 | 2019-06-26 | 1
Clients Needs | 100% | 2019-06-21 | 2019-06-25
The Deliverable given to BA | 100% | 2019-06-21 | 2019-06-25
Activitites needs to be produced | 100% | 2019-06-21 | 2019-06-25
Review of Scope Documents | 100% | 2019-06-26 | 2019-06-26
Finalizing the Scope Docs | 100% | 2019-06-26 | 2019-06-26
RACI | 100% | 2019-06-21 | 2019-06-22 | 2
WBS | 100% | 2019-06-22 | 2019-06-25 | 4
Gantt Chart | 100% | 2019-06-22 | 2019-06-25
Team Contract | 100% | 2019-06-22 | 2019-06-23
Finalizing the Tools and Technique Docs | 100% | 2019-06-26 | 2019-06-26
Risk Involved | 100% | 2019-06-21 | 2019-06-25
Project Style | 100% | 2019-06-21 | 2019-06-25 | 5
How will team perform and manage doc? | 100% | 2019-06-21 | 2019-06-22
How the success of project will be measured? | 100% | 2019-06-21 | 2019-06-25
List of assumption | 100% | 2019-06-24 | 2019-06-25
Review of Consideration Documents | 100% | 2019-06-26 | 2019-06-26
Finalizing the Consideration Docs | 100% | 2019-06-26 | 2019-06-26
Cover Letter | 100% | 2019-06-26 | 2019-06-26 | 1
Page | 100% | 2019-06-26 | 2019-06-26 | 1
Table of Content | 100% | 2019-06-26 | 2019-06-26
Header / Footer | 100% | 2019-06-26 | 2019-06-26
References | 100% | 2019-06-26 | 2019-06-26
Document History | 100% | 2019-06-26 | 2019-06-26
Elicitating VPs for assessing their current knowledge on web technologies | 100% | 2019-06-27 | 2019-07-03
Develop a training plan to train VPs | 100% | 2019-06-27 | 2019-07-03
Idetifying the Goals training plan | 100% | 2019-06-27 | 2019-07-03
Develop the final document | 100% | 2019-06-27 | 2019-07-03
Elicitate the Stakeholder to gather their current opinion | 100% | 2019-06-27 | 2019-07-03
Document their opinion | 100% | 2019-06-27 | 2019-07-03
Verify the document | 100% | 2019-06-27 | 2019-07-03
Finalizing the Document Report | 100% | 2019-06-27 | 2019-07-03
Gather the ideas from marketing team | 100% | 2019-06-27 | 2019-07-03
Document the idea | 100% | 2019-06-27 | 2019-07-03
Verify the document | 100% | 2019-06-27 | 2019-07-04
Prepare the final document | 100% | 2019-06-27 | 2019-07-04
Gather the ideas from development team | 100% | 2019-06-27 | 2019-07-03
Document their opinion and suggestions | 100% | 2019-06-27 | 2019-07-03
Verify the document | 100% | 2019-06-27 | 2019-07-04
Prepare the final document | 100% | 2019-06-27 | 2019-07-04
Idetify the features that might benefits the website | 100% | 2019-06-27 | 2019-07-01
Estimate the impact of each benefit | 100% | 2019-06-27 | 2019-07-03
Develop the final document with numeric projections of benefits of features. | 100% | 2019-06-27 | 2019-07-04
Understand the current operations of CDL | 100% | 2019-06-27 | 2019-07-03
Document the current operation process | 100% | 2019-06-27 | 2019-07-03
identify the ways to improve current operation with the help of web techs | 100% | 2019-07-03 | 2019-07-07
Develop a detailed document | 100% | 2019-06-27 | 2019-07-07
Develop the AS-IS profile for CDL operations | 100% | 2019-07-03 | 2019-07-07
Verify the AS-IS profile | 100% | 2019-07-07 | 2019-07-08
Idetify the risk that might hinder the development | 100% | 2019-07-07 | 2019-07-10
Prepare the final document | 100% | 2019-07-03 | 2019-07-10
Defining end user's and customer | 100% | 2019-06-27 | 2019-06-30
Differntiating the difference between end users and customer | 100% | 2019-06-27 | 2019-06-30
Documenting the difference | 100% | 2019-06-27 | 2019-06-30
Identifying the skills and knowledge required in website developer candidate | 100% | 2019-06-27 | 2019-06-30
Estimating the hourly wage based on those skills | 100% | 2019-06-27 | 2019-06-30
identify whether to hire full time or on contract | 100% | 2019-06-27 | 2019-06-30
Estimating the final cost of hiring web developers. | 100% | 2019-06-27 | 2019-06-30
Developing the final document | 100% | 2019-06-27 | 2019-06-30
Idetifying all the elements for first prototype draft | 100% | 2019-06-27 | 2019-07-04
Developing the prototype | 100% | 2019-06-27 | 2019-07-04
Test the prototype | 100% | 2019-06-27 | 2019-07-04
Document the prototype details | 100% | 2019-06-27 | 2019-07-04
Identify the set of specification | 100% | 2019-07-01 | 2019-07-08
Analyze the area's of improvement from the first prototype | 100% | 2019-07-04 | 2019-07-08
Develop the second prototype draft with detailed specs | 100% | 2019-07-04 | 2019-07-08
Document the prototype details | 100% | 2019-07-04 | 2019-07-09
List all the elemets used in prototype | 100% | 2019-07-04 | 2019-07-08
Estimate the time frame to deliver each element | 100% | 2019-07-07 | 2019-07-08
Verify the time frame and element | 100% | 2019-07-04 | 2019-07-08
Prepare the final document | 100% | 2019-07-04 | 2019-07-10
Idetifying the way for CDL staff to share their ideas | 100% | 2019-06-27 | 2019-06-30
Draft a plan to convey the ideas to developer | 100% | 2019-06-27 | 2019-06-30
Develop the document | 100% | 2019-06-27 | 2019-06-30
Identify the diffenet website hosting options available | 100% | 2019-06-27 | 2019-07-02
Conduct survey to sort the best 3 hosting option | 100% | 2019-06-27 | 2019-07-04
Define a criteria of comparision | 100% | 2019-06-27 | 2019-07-04
Evaluate the hosting options against those criteria | 100% | 2019-06-27 | 2019-07-07
Perpare the final Document | 100% | 2019-06-27 | 2019-07-08
Identifying how the tech support will be provided once the website is up and running | 100% | 2019-06-27 | 2019-07-09
Document the ideas | 100% | 2019-06-27 | 2019-07-09
Verify the ideas and select the best one | 100% | 2019-06-27 | 2019-07-09
Prepare the document | 100% | 2019-06-27 | 2019-07-09
Idetify the ways for furture improvement and analysis | 100% | 2019-06-27 | 2019-07-09
Verify the ideas | 100% | 2019-06-27 | 2019-07-09
Develop the document | 100% | 2019-06-27 | 2019-07-09
Developed the draft version | 100% | 2019-07-04 | 2019-07-10
Find area's of improvement | 100% | 2019-07-11 | 2019-07-15
Develop the final version | 100% | 2019-07-16 | 2019-07-17
Develop Final Presentation content | 100% | 2019-07-11 | 2019-07-14
Review Content | 100% | 2019-07-14 | 2019-07-16
Create Presentation | 100% | 2019-07-14 | 2019-07-17
Review Presentation | 100% | 2019-07-17 | 2019-07-17
Note on F6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.